PATOS-MARINZA

DEVELOPMENT PROJECT

WEEKLY MANAGEMENT MEETING REPORT

02-08 Feb 2026

10 February 2026

1.	HSSE	3

1.1	INCIDENTS	3

1.2	STATUS	3

1.3	ACTIONS	3

3.1	POLYMER CONVERSION\STIMUALTION	6

3.2	WATER FLOOD, DISPOSAL AND WI JOBS	6

3.3	JET PUMP PROJECT	6

3.4	REACTIV\RE-COMPLETION	6

3.5	DOWN WELL SITUATION AND PRODUCTION IMPACT	6

4.	COMPLIANCE AND PERMITTING & COMMUNITY RELATIONS	8

4.1	COMPLIANCE AND PERMITTING UPDATE	8

4.1.1	INSPECTION OF PRESSURE VESSEL AND HYDROCARBON TANKS	8

4.1.2	INACTIVE WELLS	8

4.1.3	OTHERS	8

4.2	COMMUNITY RELATIONS UPDATE	9

4.1.1	COMMUNITY INVESTMENTS	9

4.1.2	IMPACT MITIGATION/GRIEVANCES	9

4.1.3	OTHERS	9

5.	GEOLOGY AND DEVELOPMENT	10

6.	DEVELOPMENT & RESERVOIR ENGINEERING	11

6.1	EOR PERFORMANCE (SATURDAY – SATURDAY REPORTING CYCLE)	11

6.2	EOR	12

6.2.1 POLYMER	12

7.	WEEKLY WELL SERVICES	13

7.1	SUMMARY	13

7.2	INJECTION WELL	13

7.3	REACTIVATION	13

7.4	NEW COMPLETION	13

7.5	WORKOVERS	13

7.6	MINOR WORKOVERS	13

7.7	FLUSH BY	14

7.8	RIG LESS	14

7.9	DOWN HOLE EQUIPMENT URGENT REQUIRED	14

8.	FACILITIES AND CONSTRUCTION	15

9.	DRILLING no update	16

9.1	WELL COMPLETED	16

9.2	CURRENT DRILLING OPERATION	16

9.3	NEXT WELL PREPARATION	16

10.	TREATING AND OPERATIONS	17

11.	THERMAL OPERATIONS	20

11.1	Thermal	20

# HSSE

## INCIDENTS

| Incident Code | Date | Brief Description |
| --- | --- | --- |
| ALB0226MTI001 | 03-Feb-26 | An incident with injury has been reported by the well servicing Manager Gurim Premce at 1440 on 3rd February. The incident occurred at Superstar RSS019 rig around 11:00 AM but wasn't reported on time. While installing the wellhead one of the rig hands was injured with a bar above his eyebrow. |
| ALB0226SI002 | 06-Feb-26 | Electrical Equipment Theft |

## STATUS

| ID | Brief Description |
| --- | --- |
| 1 | Conducted monthly safety meeting with Mechanics and technical support departments |
| 2 | Two SCBA drills done at L29 A and CTF. |
| 3 | Safety induction and H2S training done for 9 employees. |

## ACTIONS

| ID | Brief Description |
| --- | --- |
| 1 | Continue cooperating with tech support team for hot work permits 14 totals. |
| 2 | 15 Site Work Inspections, 1 Lease & 3 Safety inspection, 3 WAH equipment inspections done by HS Team |
| 3 | 2 Tank trucks inspected and Truck master list updated. |
| 4 | Four safety support by the HS team at M32A, N31C, and 2 at Fieri HUB |
| 5 | Two Gas readings and one driving test performed last week. |
| 6 | 86 fire extinguishers inspected and 7 fire suppression systems. |
| 7 | Continued waste segregation and management at plastic site. |
| 8 | Continued Ecopits level monitoring and management. Ecopit 7 actual level 5 cm. Ecopit receiving materials are; Ecopit 3 - level 16.5 cm and Ecopit 8 - level 12 cm. Continued moving water from Ecopit 8 to Ecopit 3 and from Ecopit 7 to Ecopit 6. |
| 9 | Sent to NEA quarterly reporting of "Oil and gas exploration and production" permit. |
| 10 | Sent to NEA yearly reporting and environmental management plan of 2026 for Ecopit 5. |
| 11 | Sent to NEA six monthly report of Ecopit 5 and Ecopit 6 permits. |
| 12 | Continued with environmental lease inspections. |

- PRODUCTION

| Current Week | Unprorated production m3 | Reported Proration | Reported Prorated Production | Prod Lost as per Operations Night Shift Report | Prod. Lost due to Water Room |
| --- | --- | --- | --- | --- | --- |
| 2/2/2026 | 1,043.90 | 91.50% | 955.17 | 163.3 | 0 |
| 2/3/2026 | 1,050.50 | 91.60% | 962.26 | 163.5 | 0 |
| 2/4/2026 | 1,038.80 | 92.00% | 955.70 | 172 | 0 |
| 2/5/2026 | 1,042.50 | 91.80% | 957.02 | 163.5 | 0 |
| 2/6/2026 | 975.80 | 91.00% | 887.98 | 220.4 | 0 |
| 2/7/2026 | 818.60 | 89.20% | 730.19 | 374.7 | 0 |
| 2/8/2026 | 816.90 | 89.00% | 727.04 | 363 | 0 |
| Average(m3/d) | 969.57 |  | 882.19 |  |  |
| Total (m3) | 6,787.00 |  | 6175.35 | 1620.4 | 0 |
| Total Bbl |  |  | 38,842 | 10,192.19 |  |
| Last Week | Unprorated production m3 | Reported Proration | Reported Prorated Production | Prod Lost as per Operations Night Shift Report | Prod. Lost due to Water Room |
| 1/26/2026 | 1,016.00 | 89.80% | 912.37 | 199.6 | 0 |
| 1/27/2026 | 979.30 | 90.00% | 881.37 | 187.5 | 0 |
| 1/28/2026 | 1,010.10 | 90.00% | 909.09 | 168 | 0 |
| 1/29/2026 | 1,023.20 | 90.10% | 921.90 | 162.2 | 0 |
| 1/30/2026 | 1,026.50 | 90.20% | 925.90 | 159.5 | 0 |
| 1/31/2026 | 1,036.20 | 90.80% | 940.87 | 161.6 | 0 |
| 2/1/2026 | 1,043.90 | 91.00% | 949.95 | 163.3 | 0 |
| Average(m3/d) | 1,019.31 | 90.27% | 920.21 |  |  |
| Total (m3) | 7,135.20 |  | 6,441.45 | 1,201.70 | 0 |
| Total Bbl |  |  | 40,516 | 7,558.60 |  |

- ENGINEERING AND TECHNICAL

## POLYMER CONVERSION\STIMUALTION

| Well | Lease | Type | Start Date | End Date | Rig | Put on Injection | Comment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 5899 | P32A | Polymer Conversion |  |  |  |  | Postponed for 2026 (also 5836 pad P27B, 5798 pad M30A) |

## WATER FLOOD, DISPOSAL AND WI JOBS

| Well | Lease | Type | Start Date | End Date | Rig | Put on Injection | Comment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1521-M | M27 | WI job |  |  |  |  | WO program and lease ready, waiting on Rig up Service Rig |
| 5140 | I28A | Disposal |  |  |  |  | Attempt to check csg integrity. Well is flowing, we suspend op. due to no mud contracts in country to kill well. Set Packer at 732.56mKB. |

## JET PUMP PROJECT

| Well | Lease | Type | Start Date | End Date | Rig | Put on Production | Comment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3108-M | O27B | CO and RIH JP | 2/19/2020 | 2/23/2020 | RSS15 | 3/3/2020 | Cumulative 15014.1 tons oil. Gross 10m3.Net oil 6.1 tons. WC= 39% |
| 5648 | N29A | RIH JP | 12/21/2025 | 12/23/2025 | RSS19 | 12/23/2025 | Cumulative 2178.4 tons oil. Gross 44.0m3.Net oil 3.5 tons. WC= 92% |
| 5534 | M30B | CO and RIH JP | 03/29/2025 | 04/02/2025 | 80-3 | 04/16/2025 | Cumulative 1481.1 tons oil. Gross 32.0m3. Net oil 5.8 tons. WC = 82% |

## REACTIV\RE-COMPLETION

| Well | Lease | Type | Start Date | End Date | Rig | Put on Production | Comment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 5234-L2 | O32A | Reactivation |  |  |  |  | Working on WO program. |
| 5759 | P29A | Reactivation |  |  |  |  | Working on WO program |
| 957-M | SWB | Reactivation |  |  |  |  | Unable to check csg integrity due to no packer available for 5 ½ ‘’ csg size + NO tbg slim collars available. Cancel Reactivation. |

## DOWN WELL SITUATION AND PRODUCTION IMPACT

| Well | Lease | Type | Before WO | After WO | Put on Production | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| 5978 |  | Rods | 3.1 | 0.0 | 2025.10.21 | Still monitoring / shut in due to river flood |
| 5408 |  | HIT | 1.7 | 1.1 | 2025.11.10 | Still monitoring |
| 5338 |  | HIT | 2.6 | 0.9 | 2025.11.15 | Still monitoring |
| 5053 |  | HIT | 3.2 | 0.0 | 2025.12.27 | Still monitoring / Shut in due to river flood |
| 5328 |  | Rods | 3.9 | 0.0 | 2025.11.25 | Still monitoring / Shut in due to low API |
| 5796 |  | HIT | 2.6 | 0.0 |  | Wait on Service rig |
| 5025 |  | Rods | 5.3 | 3.4 | 2025.12.05 | Still monitoring |
| 5806 |  | Pump | 4.6 | 3.8 | 2025.12.05 | Still monitoring |
| 5451 |  | Pump | 2.1 | 0.0 |  | Rig on Hole |
| 5800 |  | HIT/Pump | 2.3 | 0.0 |  | Wait on Service rig |
| 5239 |  | Rods | 1.8 | 0.0 |  | Wait on Service rig |
| 5923 |  | Rods | 2.0 | 0.0 |  | Wait on Service rig |
| 5766 |  | HIT/Pump | 1.5 | 0.0 |  | Wait on Service rig |
| 5894 |  | Rod | 4.0 | 2.6 | 2025.12.23 | Still monitoring |
| 5458 |  | HIT | 2.2 | 0.0 |  | Wait on Service rig |
| 962 |  | HIT | 3.5 | 0.5 | 2026.02.06 | Still monitoring |
| 5784 |  | Pump | 3.0 | 0.0 | 2026.01.19 | Still monitoring |
| 5108 |  | HIT | 3.4 | 1.9 | 2026.01.27 | Still monitoring |
| 5257 |  | Rods/Pump | 2.5 | 0.0 |  | Wait on Service rig |
| 5190 |  | Broken centralizer | 4.8 | 2.1 | 2026.01.30 | Still monitoring |
| 6039 |  | HIT | 6.5 | 4.3 | 2026.01.27 | Still monitoring |
| 6109 |  | HIT | 5.7 | 0.0 | 2026.02.03 | Still monitoring |
| 5971 |  | Pump | 2.1 | 0.0 |  | Wait on Service rig |
| 6099 |  | Pump | 2.3 | 0.0 |  | Wait on Service rig |
| Total |  |  | 76.7 | 20.6 |  | Due to well down production impaction 56.1 tons. |

# COMPLIANCE AND PERMITTING & COMMUNITY RELATIONS

## COMPLIANCE AND PERMITTING UPDATE

### INSPECTION OF PRESSURE VESSEL AND HYDROCARBON TANKS

| ID | Brief Description |
| --- | --- |
| 1 | Ongoing the February inspection of pressure vessels and tanks. |
| 2 | Completed all reports with picture for all pressure vessels that are on February inspection list. |
| 3 | Updating the detailed inspection list with detailed information for PV. We will sent to ISHTI prior of monthly inspection by them. |
| 4 | Performing inspection by compliance for pressure vessels and tanks. |
| 5 | Saving the conformity certificates for inspected tanks. |

### INACTIVE WELLS

| ID | Brief Description |
| --- | --- |
| 1 | Ongoing the field inspections of inactive wells as per updated list. |
| 2 | Preparing inspection reports for each inspected wells. |

### OTHERS

| ID | Brief Description |  |
| --- | --- | --- |
| 1 | Identified the projects, approval of projects and acts of installations for equipment that will be on February inspection list. |  |
| 2 | Updated the equipment books for all pressure vessels which are on February inspection list. During monthly inspection will be signed by ISHTI inspectors. |  |
| 3 | Supporting other department regarding different issues. |  |

## COMMUNITY RELATIONS UPDATE

### COMMUNITY INVESTMENTS

| ID | Brief Description |
| --- | --- |
| 1 | Community investment projects: Patos and Roskovec municipality submitted their projects but as they exceeded the assigned budget the projects need to be revised. |

### IMPACT MITIGATION/GRIEVANCES

| ID | Brief Description |
| --- | --- |
| 1 | Grievances: None filed |

### OTHERS

| ID | Brief Description |
| --- | --- |
| 1 | Fier Hospital sent a request for support with materials for neonatal department. Due to company’s situation the request will not be supported. |

# GEOLOGY AND DEVELOPMENT

| PROJECT |  | CURRENT ACTIVITY/ISSUES |
| --- | --- | --- |
| DEVELOPMENT DRILLING UPDATE Well name; zone; Depth at report time; Current operation / notes. Previous well:. Current well:. Next well:. |
| Active Drilling Update | Drilling Rig |  |  |
| Reservoir Study and Development Well Optimization | - Basic study for oil field development - Further geological research based on the production dynamics of thermal wells, - Continue further study for each layer in the southern part of the oilfield - New drilling Geological design - Material for drilling |  |  |

# DEVELOPMENT & RESERVOIR ENGINEERING

- Completed the pattern performances in Central area, continue to analyze up-to-date all patterns in Southern and Northern area.

- Continue to monitor the performances of polymer producers nearby the SI polymer injectors, and identify the priority of injector for restart.

|  | Ave this week ( February 8th m3/d) |  |  | Cum production in YTD,m3 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Budget | Actual | Actual -Budget | Budget | Actual | Actual - Budget |
| Existing well |  | 777 | - |  | 31,884 | - |
| New non-thermal well |  | 0 | - |  | 0 | - |
| Polymer conversion |  | 0 | - |  | 0 | - |
| Reactivation+Stimulation |  | 0 | - |  | 0 | - |
| Thermal |  | 105 | - |  | 4,759 | - |
| Total |  | 882 | - |  | 36,643 | - |

## EOR PERFORMANCE (SATURDAY – SATURDAY REPORTING CYCLE)

|  |  | Oil Production m3/d | Oil Production m3/d | Variance |
| --- | --- | --- | --- | --- |
|  |  | Last Week | This Week | +/- (m3/d) |
| Central | PF&WF | 243.1 | 236.6 | -6.6 |
| North | PF | 47.1 | 37.1 | -10.0 |
| South | PF | 94.1 | 91.3 | -2.8 |
| EOR TOTAL | PF&WF | 384.4 | 365.0 | -19.4 |

- Two polymer producers have weekly production incremental higher than 1.5m3/d.

Water cut decrease – 5901, 5824.

- Seven polymer producers have weekly production loss equal/higher than 1.5 m3/d.

Lower runtime due to Main flow line CTF – Hub: 5036,5038,5655,5938,5939,951

High water cut after workover： 6109

## EOR

## 6.2.1 POLYMER

| ID | Brief Description |
| --- | --- |

- The Polymer Flood processes that were stopped on December 17th as well as the entire P-M oilfield due to government actions partially restarted in 11 injectors on 26 January.

- Normal operations in all the injection stations that are running. The only main facility in operation is the PSU300 at O34A (run with 65% capacity).

- Daily injection volume 860m3 (78 m3/d/well). Av daily polymer consumption is 925kg/d (1.23 bags/d)

- Continues the gradual increase in well pressures from 5% - 86% of the values ​​before injection were stopped: 5827/D4 (66%), 6108/M (100%) and 5898/D4 (75%)

6.2.2 OTHERS

| ID | Brief Description |
| --- | --- |

- Under strict monitor the WSW in G1 and G2 zone due to high reservoir energy. No changes in water quality. Max casing pressure is observed at WSW 963 (230psi)

- AMBU (Shkumbin –Seman basin agency) sent the invoices for the fresh water consumption for the period October 29th, 2025 – January 27th, 2026 (Q4-2025). Submitted the request for payment in OA system.

- A letter from Water Source Management Agency (AMBU) was received. Their request is the information on the quality of water resources. Working with the other department to prepare the material.

- Certification of WSW flowmeter calibration. GDM has not yet uploaded the invoice for the calibration of WSW flowmeters in the system but continue to ask prepayment. We are still waiting

- Training and operations on oil production wells monitored by EOR operators continue normal.

- Hot water with Surfactant and Viscosity Reducer, Huff & Puff.

- 5577/G4: to recover 1252m3; FDT 326m; Net 1.9m3/d

- 5284/G4: to recover 1851m3; SI due to main line CTF-HUB

- 5836/D3L: to recover 1254m3; FDT 221m; Net 2.9m3/d

- 5614/G6: to recover 13819m3; on soaking time

6.2.3  NEW CONVERSION 2025

| Wells for Conversion | Injection well | PAD | Mixing Area | First Injection Date | Comments |
| --- | --- | --- | --- | --- | --- |
| 1 | 5891/D3U | O32B | S | February 15 | OpEx |
| 2 | 5982/D5 | N31B | S+SW | February 22 OpEx |  |
| 3 | 5568/D3U | O35A | S | February 18 Injecting with temporary system OpEx |  |
| 4 | 5797/M0U | M30A | S+SW | March 25 OpEx |  |
| 5 | 5237/L1,L2-D3 | L31A | SW | March 24 OpEx |  |
| 6 | 6189/D3U | M37A | S | June 11 Injecting with temporary system |  |

# WEEKLY WELL SERVICES

## SUMMARY

| Single Rig SS18 or SS19 | 2 jobs completed by Single Rig SS18 or SS19 |
| --- | --- |
| Flush by Rig SS17 | 5 jobs completed by Flush by rig SS17 |
| Rig less Jobs | 3 wells/jobs - completed by Rig less |

## INJECTION WELL

| Type | Comment |
| --- | --- |
| Injector wells | None |

## REACTIVATION

| Type | Comment |
| --- | --- |
| Reactivation wells | None |

## NEW COMPLETION

| Type | Comment |
| --- | --- |
| New drilled wells | None |

## WORKOVERS

| Type | Comment |
| --- | --- |
| WIII wells | None |

## MINOR WORKOVERS

| Type |  | Comment |
| --- | --- | --- |
| Clean out/pump change/hole in tubing/parted rod/corod and other routine jobs. | 6109 HIT, clean out & pump change, 962M HIT & change equipment, re run same pump, 5451 clean out & pump change, jobs in red underway. |  |
| Recover rods/corod/tubing |  | None |
| String check, surface rod/corod or fish, flushes, rod lift, check space out, pressure test and other small jobs. |  | 6129 change polish rod(thermal well), 5642 broken polish rod, 6060 parted rod, fish & repair string, 6187 thermal well, flush tbg and csg, jobs in red underway |
| Change top drive |  | 5981(Oil Lift) |
| Recover surface equipment |  | None |
| Convert Grenco drive head to Oil Lift |  | None |
| Other |  | None |

## FLUSH BY

| Type | Comment |
| --- | --- |
| Flush By(over torque) | None |

## RIG LESS

| Type | Comment |
| --- | --- |
| Install well head | None |
| ESP | None |
| Coil Tubing operation | None |
| CoRod injector operation | None |
| Other | 6129/6187 thermal well, changed packing seals on stuffing box. 1359M source water well, over flowing, install nipples and cable gland seals and isolate well as per polymer team request. |

## DOWN HOLE EQUIPMENT URGENT REQUIRED

| Type | Comment |
| --- | --- |
| Normal tbg hanger 4.5” | Recommend to order from previous supplier 01-46TBGHGR(Compass) |

# FACILITIES AND CONSTRUCTION

| Project | % complete |  | Current Activity/Issues |  |
| --- | --- | --- | --- | --- |
| Insulating crew |  |  | - Paint the lines around the field. |  |
| Sat#3 8” emulsion line replacement |  | 60 |  | On going with preparations. |
| Scale new construction installation |  | 30 |  | Waiting Tunamar to finish with the last installations |
| L26c clean mud at security cameras. |  | 100 |  | This site has been cleaned. Ready for security. |
| CR request |  |  |  | On going with preparing the cost estimation. |

# DRILLING no update

## WELL COMPLETED

| RIG NAME | WELL/PAD/CELLAR | Planned TD/ Actual TD | DETAILS |
| --- | --- | --- | --- |
| - | - | - | - |

## CURRENT DRILLING OPERATION

| RIG NAME | WELL/PAD/CELLAR | Planned TD/ Current DEPTH | CURRENT OPERATION |
| --- | --- | --- | --- |

## NEXT WELL PREPARATION

| RIG NAME | WELL/PAD/CELLAR | SRAs/Site Preparation | AFE | PROGRAM |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | GEO/ DIRECTIONAL | DRLG PROGRAM |

# TREATING AND OPERATIONS

#### TREATING

|  | Treating |  |  |
| --- | --- | --- | --- |
| Last week This week Variable |  |  |  |
| Pad D shipping WCT % | 16.5 | 13.6 | -2.9 |
| Pad H shipping WCT % | 11.3 | 10.6 | -0.7 |
| Sat#3 shipping WCT % | 13.3 | 13.4 | 0.1 |
| CTF shipping WCT % | 2 | 2.1 | 0.1 |
| Average Fier Hub WCT % | 1.8 | 1.7 | -0.1 |
| Average Fier Hub API | 8.5 | 8.61 | 0.11 |
| CTF – HUB Balance MT ( min ) |  |  | - |
| CTF – HUB Balance MT ( max ) |  |  | - |
| CTF – HUB Balance total MT |  |  | - |
| Average Diluent Usage, m3 | 13.9 | 11.64 | -2.26 |
| Average Diluent / Net Oil Production, % |  |  |  |
| Average Demulsifier Dosage, ppm |  |  |  |

10.2	M28D , SLUDGE & AGING OIL FACILITY TREATMENT

|  |  | M28D |  |  |  |
| --- | --- | --- | --- | --- | --- |
| IN |  |  |  | OUT |  |
|  | YTD | This Week |  | YTD | This Week |
| Product Received,m3 |  | 0 | Blend Oil Sales, m3 |  | 0 |
| Diluent Supply,m3 |  | 0 |  |  |  |
| Heavy Water Supply, m3 |  | 0 | Water out, m3 |  | 0 |
| Process continue stopped due to low inventory of diluent |  |  |  |  |  |
| Sludge Treatment Facility |  |  |  |  |  |
| IN |  |  |  | OUT |  |
|  | YTD | This Week |  | YTD | This Week |
| Product Received,m3 |  | 0 | Blend Oil Sales, m3 |  | 0 |
| Diluent Supply m3 |  | 0 |  |  |  |
| Heavy Water Supply, m3 |  | 0 | Water Out, m3 |  | 0 |
| Eco pit water treated with chemicals. Process continue stopped. |  |  |  | 39,084 | 810 m³ |

| Skim Fac. and Aging oil Facility SOAR |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| IN |  |  | OUT |  |  |
| YTD |  | This Week | YTD |  | This Week |
| Product Received m3 | 5,084 | 339 | Blend Oil Sales, m3 2225 |  | 201 |
| Diluent Supply,m3 | - | - | - |  | - |
| Heavy Water Used, m3 | 7,300 | 374 | Water out, m3 8441 |  | 464 |
| On 09th of Feb. (night shift) Sotu stopped due to low gas pressure. |  |  |  |  |  |

#### 10.3  MTD CRUDE SALES

|  | MTD Crude Sales |  |
| --- | --- | --- |
| Alb Petrol PEP/ASP, m3 & WCT% | 677.31 | 1.7% |
| Bitex Elbasan, m3 & WCT% | - |  |
| AL Global, m3 & WCT% | - |  |
| PIA Exports, MT & WCT% | 21,164.87 | 2 .4% |

10.4  IN FIELD FLUID TRANSPORTATION

| Average Daily Fluid Transportation, m3 |  | Last week |  | This week | Varies |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Back Loads to Field |  |  |  |  |  |  |  |
|  | Last week | This Week |  |  | Last week | This Week |  |
| Back Loads From Fier To Field, m3 | - |  | Average Water Cut , % |  | - |  |  |
| Back Loads From PIA To Field, m3 | 103 | 161.5 | Average Water Cut , % |  | 14.5% | 33.8% 9m3 fw |  |

10.5  CTF Gas Flotation Unit:

| Inlet OIW | Outlet OIW | Inlet TSS | Outlet TSS | G31A OIW | G31A TSS | I28A OIW | I28A TSS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 268 ppm | 61.3 ppm | 60.7 mg/l | 47.5 mg/l | 50 ppm | 38.4 mg/l | 45.3 ppm | 40.3 mg/l |

10.6 OTHER

Pad H: Diluent usage  1 m3/day.

GOR#3, still bypassed.

Gas pressure low in all facilities.

Sat#3: Diluent usage  4 m3/day.

Pad D: Diluent usage  1 m3/day.

CTF: Hauled out treated oil to field cascades, will start to hauled back the oil.

Water disposal

2468 increased injection pressure from 2400 psi up to 2800 psi.

N-24-A/K-27-A/H-27-A  shut in, low water levels.

20 m3 skim/slop removed from water tanks in disposal pads.

Chemical

Use diesel as defoamer

At G32-A the viscosity reducer was changed from PAW-4 to BHY-8021.

- THERMAL OPERATIONS

  - Thermal

Weekly Data  on Thermal Average Production (as per night shift)

| Well | Gross (m3) | Net oil (m3) | BSW (%) | Loading (m3) | Chemical in tbg/csg(litra) |  | Comment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 6188 | 26.4 | 3.9 | 55% | 8 | 0 |  | Tight belts, Test 07/02/26, Flow line to Pad-D |
| 6168 | 0 | 0 | 0% | 0 | 0 |  | Shut in 2026/01/02. Preparing for steam injection, Low API. |
| 6166 | 30.7 | 4.6 | 67% | 5.4 | 0 |  | Test 07/02/26, Flow line to Pad-D |
| 6165 | 85 | 18.7 | 78% | 0 | 0 |  | Test 04/02/2026, Flow line to Pad-D |
| 6163 | 0 | 0 | % | 0 | 0 |  | Shut in due to uneconomic at 03/03/2025 |
| 6169 | 61.9 | 13.3 | 71% | 4.6 | 0 |  | Test 05/02/26, Flow line to Pad-D |
| 6187 | 36 | 10 | 69% | 2.7 | 0 |  | Flush by 51m3 water, Started 30hz, On Test 08/02/25 speed up 2+2hz |
| 6161 | 0 | 0 | % | 0 | 0 |  | Shut in due to uneconomic at 17/01/2026 |
| 5943 | 13.9 | 4.2 | 55% | 2 | 0 |  | Test 05/02/26 - Flow line to Pad - D |
| 6186 | 0 | 0 | % | 0 | 0 |  | Stopped 12/12/2025 @14:00, Low API |
| 6185 | 47 | 12.7 | 56% | 8 | 0 |  | Test 29/01/26, Flow line to Pad - D |
| 6129 | 54 | 0 | 100% | 0 | 0 |  | SWB. |
| 5376 | 48.7 | 14.5 | 56% | 7 | 0 |  | Test 23/01/26, Flow line to Pad-D |
| 5377 | 0 | 0 | % | 0 | 0 |  | Shut in 2026/01/05. Preparing for steam injection. |
| 6036 | 16 | 8.5 | 47% | 0 | 0 |  | Test 05/02/26 - Flow line to Pad-D |
| 5576 | 0 | 0 | % | 0 | 0 |  | No inflow. |
| 5886 | 14 | 4.2 | 20% | 7 | 0 |  | SWB |
| 5790 | 0 | 0 | % | 4 | 0 |  | Shut in 2026/01/07. Low API. |
| 6111 | 0 | 0 | 0% | 0 | 0 |  | Preparing for steam injection |
| 6065 | 23 | 7.3 | 42% | 6 | 0 |  | Test 16/01/26, Flowline to Pad-D |
| 5186 | 26 | 10.9 | 58% | 0 | 0 |  | Test 02/02/26 |
| Total | 3377 | 789.2 | 59.3% |  |  |  |  |
| Weekly data on Thermal Average Steam Injection |  |  |  |  |  |  |  |
| Well | Rate (t/h) | Pressure(psi) | Temp(OC) | Dryness (%) | Total Steam Injection(m3) |  | Comment |
|  | 0 | 0 | 0 | 0 0 |  |  |  |
|  | 0 | 0 | 0 | 0 0 |  |  |  |
|  | 0 | 0 | 0 | 0 0 |  |  |  |

Brief Description

- Total Thermal wells on production for this week, 13 wells. - Well 6168-Preparing for steam injection, required N2 injection. - Well 6111-Preparing for steam, required N2 injection. - Well 6186-Stop well 2025-12-12 due to low API. - Well 5790-Stop well 2026-01-07 due to low API. - Well 5377-Stop well 2026-01-05 and prepare for steam injection. - Well 6161- Shutt in on 2026-01-16, due to uneconomic. - Well 6129-Fluid production 53m3/d with 100% water cut,total fluid production after this steam circle is 790m3. - Wells 5576-Well is down due to no inflow. - Well 6163- Shutt in on 03/03/2025, due to uneconomic. - The average net daily oil for the this week = 112.7tons/d. - The total net production for this week was 789.2 tons which is 88 t less than previous week. The main changes on the production have been: - -68t from well 6187, Stop production and flush well with hot water. - Injection & Boiler - Boiler nr 1, M30C pad, Waiting for the employee service contract. - Boiler nr 2, O30A pad, Waiting for the employee service contract. - Boiler nr 3, N29E pad , Waiting for the employee service contract.